DELIVERY ROADMAP

# AI Customer Support Platform

Task 5 — Development & Implementation Plan v1.0

An execution-focused roadmap for product, engineering, AI, integrations, QA, security, and operations. Designed for a 20-person team building a multi-tenant SaaS platform across chat, email, and inbound voice.

| Plan detail | Baseline |
| --- | --- |
| Planning horizon | Approximately 16–20 weeks to a controlled pilot, subject to team skills, provider access, and scope. |
| Sprint cadence | Two-week sprints; one integrated demo per sprint. |
| Delivery strategy | Vertical slices; chat first for fastest feedback, then email and voice, with all three included in the initial release plan. |
| Architecture assumption | Modular monolith + separately deployed workers and channel adapters; managed infrastructure. |
| Quality principle | No autonomous customer-facing rollout until security, evaluation, handoff, and rollback gates pass. |

# Executive summary

Build the complete support workflow before broadening automation. The first meaningful milestone is not a polished dashboard or a sophisticated AI prompt. It is one customer conversation that enters through a channel, gets a grounded answer or safe handoff, reaches an agent with full context, resolves correctly, and produces reliable operational data.

# 1. Delivery principles

Work in two-week sprints and demonstrate integrated software, not just completed tickets.

Build a thin vertical slice across frontend, API, database, AI, channel adapter, and QA before scaling individual modules.

Keep one canonical case and conversation model for chat, email, and voice.

Use feature flags to enable capabilities and AI autonomy per tenant and per channel.

Treat security, observability, accessibility, and AI evaluation as work in every sprint—not final-stage cleanup.

Prefer managed infrastructure and a modular codebase until real scale justifies more operational complexity.

Make human handoff, provider outage, model failure, retries, and data deletion first-class product behavior.

# 2. Roadmap and milestones

| Phase / timing | Primary outcome | Major deliverables | Exit gate |
| --- | --- | --- | --- |
| Phase 0 — Week 1 | Confirm scope and reduce unknowns | Provider spikes, ADRs, backlog, test strategy, risk register | Critical provider/latency/security unknowns measured; MVP scope signed off. |
| Phase 1 — Weeks 2–4 | Secure platform foundation | CI/CD, auth, tenant isolation, roles, schema, audit, observability, queue/outbox | Cross-tenant negative tests pass; deploy/rollback and backups demonstrated. |
| Phase 2 — Weeks 5–8 | Chat end-to-end slice | Widget, inbox, case workspace, knowledge ingestion, grounded AI, handoff | A real chat test can resolve or escalate and be completed by an agent. |
| Phase 3 — Weeks 9–11 | Email support workflow | Inbound/outbound, threading, delivery states, retry/DLQ, attachment controls | Duplicate, bounce, threading and provider outage tests pass. |
| Phase 4 — Weeks 12–15 | Inbound voice workflow | Number setup, speech pipeline, AI turn handling, transfer, consent, fallback | Real test calls meet agreed latency and transfer reliability thresholds. |
| Phase 5 — Weeks 16–18 | Tenant configuration and quality | Onboarding, policy publish/rollback, evaluation dashboard, analytics, quotas | A pilot tenant can configure, test, publish, pause and inspect automation. |
| Phase 6 — Weeks 19–20+ | Controlled pilot / GA readiness | Security review, load tests, runbooks, restore drill, customer feedback | Go/no-go checklist approved; critical defects closed; pilot owner assigned. |

Schedule is an initial planning estimate, not a guarantee. Provider onboarding, telephony requirements, compliance review, team experience, and changes in scope can materially shift the timeline. Do not remove safety gates to protect a date.

# 3. Sprint-by-sprint plan

| Sprint | Build focus | Demo / acceptance target |
| --- | --- | --- |
| S0 — 1 week | Discovery and technical spikes | Recorded decisions for backend, tenant isolation, queue, email provider, voice provider, model/RAG and budget. |
| S1 — 2 weeks | Repo, CI, environments, auth, tenant membership, RBAC skeleton | Deployable app; user can sign in; server resolves tenant from authorized membership. |
| S2 — 2 weeks | Core case/message schema, API conventions, audit, outbox/queue, observability | Create/list case; duplicate event is safely deduplicated; correlation ID visible in logs. |
| S3 — 2 weeks | Chat widget, session handling, channel adapter, basic agent inbox | Customer message appears once in the correct tenant's inbox. |
| S4 — 2 weeks | Knowledge ingestion, retrieval, AI policy, grounded response, handoff | Known answer cites approved source; unknown answer safely escalates; agent sees summary. |
| S5 — 2 weeks | Agent case workspace, assignment, SLA basics, customer timeline, resolution | Agent replies, resolves, reopens as configured; events and metrics update. |
| S6 — 2 weeks | Email inbound/outbound, threading, delivery state, retries | Email thread remains linked; bounce/duplicate/outage cases recover safely. |
| S7 — 2 weeks | Voice provider integration, call state, speech pipeline, transfer, fallback | Test call answered; handoff transfer succeeds or safe fallback runs. |
| S8 — 2 weeks | Tenant setup wizard, AI policy versioning, test suite, publish/rollback | Admin changes a policy, tests it, publishes, and rolls back. |
| S9 — 2 weeks | Analytics, quotas, security hardening, accessibility, pilot onboarding | Pilot checklist, operational dashboards, runbooks, and acceptance sign-off. |

# 4. Team ownership and accountability

Assign one directly responsible individual (DRI) per workstream. The DRI coordinates dependencies and signs off on readiness; they do not need to implement every task personally.

| Workstream | Indicative staffing | Accountable outputs |
| --- | --- | --- |
| Product & UX | 2 | Backlog, workflow decisions, prototypes, acceptance criteria, pilot feedback. |
| Frontend | 3 | Admin console, agent workspace, chat widget, component system, accessibility. |
| Core backend | 4 | Tenancy, identity integration, cases/messages, routing, API, audit and configuration. |
| AI & knowledge | 3 | Orchestration, RAG, safety checks, evaluation sets, model/provider adapter. |
| Channel integrations | 3 | Email, chat integration support, telephony/voice runtime and provider tests. |
| QA / automation | 2 | Test plans, contract tests, E2E automation, regression, security and load coordination. |
| Platform / security | 2 | Cloud, CI/CD, secrets, monitoring, backups, incident and security controls. |
| Engineering/product lead | 1 | Architecture decisions, sequencing, scope, delivery risk, cross-team blockers. |

## Ownership rules

Every feature has a single DRI, a reviewer, QA coverage, telemetry, and documented failure behavior.

Security and QA can block release for tenant isolation, data exposure, or unsafe automation issues.

Channel integration owners maintain provider contract tests and a troubleshooting runbook.

AI owner owns evaluation quality and versioning—not only prompt construction.

Engineering lead resolves cross-module API and schema disputes quickly and records decisions.

# 5. Work breakdown structure

## 5.1 Platform foundation

Create repositories, branching strategy, code review rules, lint/type checks, secret scanning, dependency scanning, and CI pipelines.

Provision development, staging, and production environments using infrastructure as code.

Implement users, tenants, memberships, role permissions, tenant resolution, session management and audit events.

Create migrations for customers, cases, conversations, messages, queues, channel connections and configuration versions.

Implement API error envelope, validation, pagination, rate limiting, correlation IDs and idempotency support.

Set up managed database, durable queue, private object storage, secrets management, logs, metrics and traces.

Document deployment, rollback, backup, restore, incident severity and environment access.

## 5.2 Chat and unified case workflow

Build secure widget session and origin allowlist; add abuse/rate limits and session expiry.

Normalize inbound messages into canonical message events and persist before processing.

Implement agent inbox filters, case assignment, reply composer, internal notes, status changes and audit trail.

Build knowledge source registration, parsing, chunking, embedding, publication state and retrieval tests.

Implement policy → retrieve → generate → validate → answer/clarify/handoff pipeline.

Create handoff state machine with reason, summary, destination queue, waiting state, agent acceptance and timeout behavior.

Add channel failure banners, retry behavior, message delivery status and customer-facing fallback copy.

## 5.3 Email workflow

Select one supported provider/inbound path; validate authentication and webhook signature.

Parse message headers, body, attachments, thread identifiers, auto-replies and bounce events.

Deduplicate provider events; use conservative threading and do not merge cases by subject alone.

Implement outbound send, reply-to identity, threading headers, status tracking, retry policy and dead-letter operations.

Add attachment size/type limits, private storage, scanning where practical, and retention/deletion behavior.

Test send failure, bounced message, delayed webhook, duplicate webhook, out-of-order events and mailbox disconnection.

## 5.4 Voice workflow

Validate provider number provisioning, inbound call webhooks, audio streaming, transcription, transfer and call completion events.

Implement call/session state transitions and link calls to the canonical case model.

Configure greeting, AI disclosure, language, consent, recording/transcription policy and business hours.

Implement turn-taking, interruption/barge-in behavior if supported, timeouts, latency telemetry and safe no-answer behavior.

Implement human transfer with queue/summary context; test transfer rejection, queue timeout and provider disconnect.

Restrict access to recordings/transcripts separately; implement retention and deletion rules.

## 5.5 Tenant setup, administration and analytics

Build setup wizard with required/optional steps and provider test checks.

Add tenant-configured AI autonomy modes, allowed topics/actions, escalation triggers, language and channel-specific rules.

Implement config draft → test → publish → rollback with version IDs and audit events.

Track channel health, case outcomes, handoff acceptance, SLA, model latency, cost and evaluation outcomes.

Implement tenant quotas, rate limits, alerts, usage reporting and safe emergency pause controls.

# 6. Backlog structure and example user stories

| Epic | Example story | Acceptance criteria |
| --- | --- | --- |
| Tenant security | As an admin, I can invite a user with a defined role. | Invitation expires safely; role is enforced server-side; action is audited. |
| Unified inbox | As an agent, I can see assigned and unassigned cases across channels. | Filters work; channel is clear; permissions and tenant scope are enforced. |
| Grounded AI | As a customer, I receive answers based on approved support content. | Answer stores source/version references; absent or conflicting sources trigger fallback. |
| Human handoff | As a customer, I can request a human without repeating my issue. | Transcript/thread and summary are preserved; queue and handoff state are visible. |
| Email | As an agent, I can reply in an existing email thread. | Threading is preserved; send status is tracked; duplicate webhooks do not duplicate replies. |
| Voice | As a caller, I can be transferred to a person when requested. | Transfer is attempted; timeout/rejection leads to a clear fallback and a case record. |
| AI configuration | As an admin, I can test and publish a new AI policy. | Publishing requires permission and passing checks; version is auditable and reversible. |
| Quality analytics | As an operations lead, I can find recurring AI failures. | Review data has access controls; metric definitions and sample size are visible. |

# 7. Definition of Ready and Definition of Done

## Definition of Ready

☐ User/problem and intended outcome are clear.

☐ Acceptance criteria include success, error, permission-denied and relevant edge cases.

☐ API/data contracts and dependencies are known or explicitly tracked.

☐ Design and copy are available for user-facing behavior.

☐ Security, privacy, retention, analytics and accessibility implications have been considered.

☐ The task is small enough to review and complete within a sprint or is split.

## Definition of Done

☐ Code is reviewed, merged, and passes CI, lint, type, unit and relevant integration tests.

☐ Authorization and tenant-isolation behavior is tested, including negative cases.

☐ Loading, empty, success, error, retry and provider-degraded states are handled where relevant.

☐ Telemetry, correlation IDs and actionable alerts are included without leaking sensitive content.

☐ API contracts, migration notes, configuration and operational documentation are updated.

☐ QA verifies acceptance criteria in a representative environment.

☐ Feature flag, rollback/disable path, and support runbook are ready for customer-facing features.

# 8. Testing and release gates

| Gate | Required evidence | Release blocker examples |
| --- | --- | --- |
| Gate A — PR/CI | Unit tests, lint, type checks, secret/dependency scans, migration validation | Broken build, exposed secret, unreviewed schema change. |
| Gate B — Integration | DB/queue/outbox, provider adapters, signatures, idempotency, permission tests | Cross-tenant access, duplicate customer send, lost job. |
| Gate C — E2E | Chat, email, voice happy path and failure path; agent handoff and resolution | Lost context, unsafe answer, failed fallback. |
| Gate D — AI quality | Representative regression set, groundedness checks, prompt-injection and sensitive-request tests | Mandatory handoff ignored; material unsupported claim; regression beyond agreed threshold. |
| Gate E — Pilot readiness | Load/latency results, backup restore, alerts, runbooks, privacy/retention review | No kill switch, untested restore, unknown incident owner. |

## Minimum pre-pilot scenarios

☐ Known chat question → sourced answer → customer confirms resolution.

☐ Unknown question → safe clarification/fallback → handoff with summary.

☐ Explicit human request → no AI obstruction → correct queue.

☐ Email duplicate webhook → one case/message; provider bounce → visible failure and safe retry policy.

☐ Voice transfer succeeds; transfer fails → configured callback/voicemail/alternate fallback.

☐ Model timeout/provider outage → AI automation pauses or routes safely; no false success.

☐ Tenant A cannot access tenant B cases, sources, attachments, embeddings, reports or recordings.

☐ Published knowledge update changes answers only after approval; rollback restores prior behavior.

☐ Customer deletion propagates to operational content, files, indexes and applicable downstream systems.

☐ Rate-limit/abuse spike does not cause unbounded spend or degrade all tenants.

# 9. AI evaluation and autonomy rollout

| Stage | Allowed behavior | Promotion criteria |
| --- | --- | --- |
| Internal offline | Replay approved test set; no customer-facing sends. | Evaluation harness, source attribution, safety tests and baseline results exist. |
| Shadow mode | AI produces candidate answers while humans remain responsible; compare without auto-send. | Sufficient representative samples; failure categories reviewed; no critical safety failures. |
| Agent assist | AI suggests summaries and drafts; agent approves send. | Usability feedback, quality improvement, access controls and audit validated. |
| Limited auto-send | Only low-risk, explicitly allowed topics/channels; tenant-specific feature flag. | Agreed quality thresholds, safe fallback, handoff success, cost cap, kill switch and monitoring. |
| Expanded automation | Broader topic coverage only after evidence and customer approval. | Stable outcomes across recontact, complaints, groundedness, handoff and channel reliability. |

Do not define success as 'AI handled X% of messages' alone. Track confirmed resolution, repeat contact, customer feedback, answer quality, inappropriate automation, handoff acceptance, and cost per resolved case.

# 10. Delivery management and ceremonies

| Cadence | Meeting / artifact | Purpose |
| --- | --- | --- |
| Daily | 15-minute team sync | Blockers, dependency coordination, incident awareness. |
| Weekly | Product/engineering backlog review | Clarify next sprint work, acceptance criteria and risk. |
| Every 2 weeks | Sprint planning and review/demo | Commit to a realistic goal; demo working software to stakeholders. |
| Every 2 weeks | Retrospective | Choose 1–2 measurable improvements to delivery quality. |
| Weekly during integrations | Provider spike / integration review | Surface API changes, sandbox limits, webhook and transfer issues. |
| Every release | Go/no-go review | QA, security, AI quality, operational readiness and rollback approval. |

## Recommended work tracking fields

Epic, story, owner, reviewer, priority, estimate, sprint, dependency, acceptance criteria.

Tenant/channel scope, security/privacy classification, analytics event, test plan, rollout flag.

Status, blocked reason, code review, QA result, release note and rollback plan.

# 11. Delivery risks and mitigations

| Risk | Mitigation |
| --- | --- |
| Voice integration consumes schedule | Run provider spike in Week 1; keep a named voice owner; lock a fallback route before feature expansion. |
| Scope grows into a generic automation builder | Protect MVP boundaries; defer advanced workflow canvas and broad integration marketplace. |
| AI quality is unreliable | Use approved knowledge, versioned prompts/policies, regression evaluation and limited autonomy rollout. |
| Security is postponed | Make tenant isolation and sensitive-data tests CI gates from Phase 1. |
| Frontend and backend drift | Define OpenAPI contracts and shared schemas; demo integrated slices every sprint. |
| Provider sandbox differs from production | Schedule real end-to-end provider tests and staged number/mailbox activation early. |
| Unclear ownership | Every module and feature has a DRI; cross-team dependencies are visible in the sprint plan. |
| Production support is an afterthought | Build alerts, runbooks, backup/restore, pause controls and incident ownership before pilot. |

# 12. Pilot readiness checklist

☐ Pilot customer, use cases, channels, business hours and escalation queues are agreed.

☐ Approved knowledge base has owners, publication dates, test questions and rollback plan.

☐ Chat, email and voice provider credentials are stored securely and test flows pass.

☐ AI autonomy is conservative by default; mandatory handoff and emergency pause have been tested.

☐ Agent training, manager dashboard, case ownership and escalation coverage are ready.

☐ Privacy notices, recording/transcription settings, retention, data processing terms and subprocessors are reviewed.

☐ Security tests, access review, backup restore, incident response and support escalation paths are complete.

☐ Success metrics and stop conditions are documented before the pilot begins.

☐ Pilot has a named internal owner, daily review cadence at the start, and customer feedback channel.

# 13. Pilot metrics and stop conditions

| Metric | How to interpret | Suggested operating rule |
| --- | --- | --- |
| Confirmed resolution | Customer or workflow evidence indicates issue was solved | Measure separately from AI-handled and AI-answered. |
| Repeat contact / reopen | Customer returns about the same issue within a defined window | A rising rate can indicate false resolution or poor answers. |
| Handoff success | Eligible handoffs are accepted by a human within the configured target | Alert on queue overflow, transfer failure and long wait. |
| Grounded answer quality | Sampled responses are supported by approved sources and policy | Critical unsupported or unsafe answer triggers review and possible pause. |
| Channel reliability | Inbound events processed and outbound messages/calls delivered correctly | Provider failure must activate documented fallback. |
| Latency | End-to-end p50/p95 by channel, plus stage-level timing | Agree channel-specific targets after real baseline tests. |
| Cost per confirmed resolution | Model, telephony, email, infrastructure and support costs / confirmed resolutions | Set tenant budget alerts and investigate abnormal usage. |

Before the pilot, set numerical thresholds from your baseline and customer agreement. Pause auto-send for a tenant/channel if critical safety issues occur, handoff breaks, provider failures are uncontained, or cost/latency exceeds agreed limits.

# 14. First 10 working days — immediate action plan

| Day | Actions | Output |
| --- | --- | --- |
| 1 | Appoint owners; confirm target pilot segment and MVP boundary. | Named DRIs; scope and risk register. |
| 2 | Choose backend shortlist and database/queue approach; start ADRs. | Architecture decisions in review. |
| 3 | Run email provider spike: inbound event, threading, outbound test. | Provider capability notes and sample contracts. |
| 4 | Run voice spike: inbound call, streaming/transcription, transfer, event callbacks. | Latency and transfer report; fallback plan. |
| 5 | Run RAG/model spike with approved FAQ and failure cases. | Baseline quality/cost/latency and evaluation set. |
| 6 | Finalize tenant isolation strategy and threat scenarios. | Data-flow diagram; negative security test plan. |
| 7 | Create repos, CI checks, development environment and secrets workflow. | First deployable skeleton. |
| 8 | Implement tenant-aware identity/membership and basic authorization. | Sign-in and permission tests. |
| 9 | Implement initial case/message schema, migrations and API contracts. | Create/list case API with tests. |
| 10 | Demonstrate an integrated vertical slice skeleton and review risks. | Sprint 1 backlog ready; blockers assigned. |

# 15. Definition of success for Task 5

☐ The team has named owners, a prioritized backlog and a realistic sprint plan.

☐ The platform can be deployed repeatedly and safely into controlled environments.

☐ A secure, tenant-aware case/message foundation exists.

☐ Chat demonstrates the end-to-end AI → source-grounded response or handoff → agent resolution workflow.

☐ Email and voice are implemented against the same case model with provider-specific reliability tests.

☐ AI autonomy is versioned, evaluated, tenant-configurable and reversible.

☐ A pilot can be operated with metrics, alerting, runbooks, backup/restore and clear stop conditions.

# Final recommendation

The first engineering milestone should be a thin vertical slice, not a large batch of disconnected features. Prove the complete chat journey with secure tenancy, approved knowledge, safe escalation, agent resolution, observability and regression tests. Then reuse the same case model and operating patterns for email and voice. Keep voice-provider validation early because telephony constraints can materially affect the architecture and timeline.

This plan is a working baseline. Re-estimate after technical spikes and the first two sprints. Any production use must be reviewed for applicable privacy, recording/consent, security, retention, data residency and customer-contract requirements.